## Métricas
Métricas por issue
Issue |  |  |  | Backlog |  |  | Métricas (hs)
Tipo | Nombre | Número | Entrega | To Do | In Progress | Done | Lead Time | Cycle Time | Touch Time
Bug | Baja de géneros | 31 | 2 | 2023-04-03 18:00 | 2023-04-17 22:30 | 2023-04-18 20:25 | 362.4167 | 21.9167 | 0.5
Bug | Botón de sign up no hace nada | 15 | 2 | 2023-04-03 18:00 | 2023-04-15 16:30 | 2023-04-18 20:25 | 362.4167 | 75.9167 | 4.3333
User Story | Gestión de Snacks - Frontend | 53 | 3 | 2023-05-07 14:00 | 2023-05-07 14:00 | 2023-05-12 22:10 | 128.1667 | 128.1667 | 2
User Story | Gestión de Snacks - Backend | 63 | 3 | 2023-05-06 12:40 | 2023-05-06 13:00 | 2023-05-12 22:10 | 153.5 | 153.1667 | 21.5
User Story | Agregar Snack a compra de ticket - Frontend | 55 | 3 | 2023-05-07 16:00 | 2023-05-07 16:00 | 2023-05-12 22:10 | 126.1667 | 126.1667 | 2
User Story | Agregar Snack a compra de ticket - Backend | 62 | 3 | 2023-05-06 12:40 | 2023-05-11 22:00 | 2023-05-12 22:10 | 153.5 | 24.1667 | 9
User Story | Crear Test explotario automático con Selenium |  | 4 |  |  |  | 0 | 0 | 0
[7 empty] | 214.3611 | 88.25 | 6.5556 | AVG (hs)
[7 empty] | 8.9317 | 3.6771 | 0.27315 | AVG (días)
Métricas por entrega | [10 empty] | Entrega 2 |  |  |  |  | Cumulative Flow Diagram (CFD)
Entrega | AVG Lead Time (hs) | AVG Cycle Time (hs) | AVG Touch Time (hs) | Eficiencia de flujo | Estado actual | Throughput (por día) |  |  |  |  | Fecha | Day | To do | In Progress | Done
2 | 362.4167 | 48.9167 | 2.4167 | 0.66682 | Valor no deseado | 0.19867 |  |  |  |  | 2023-04-03 | 1 | 2 | 0 | 0
3 | 140.3333 | 107.9167 | 8.625 | 6.1461 | Valor normal | 0.51306 |  |  |  |  | 2023-04-04 | 2 | 2 | 0 | 0
4 |  |  |  | #DIV/0! |  | #DIV/0! |  |  |  |  | 2023-04-05 | 3 | 2 | 0 | 0
WIP | 3 | [9 empty] | 2023-04-06 | 4 | 2 | 0 | 0
[11 empty] | 2023-04-07 | 5 | 2 | 0 | 0
[11 empty] | 2023-04-08 | 6 | 2 | 0 | 0
[11 empty] | 2023-04-09 | 7 | 2 | 0 | 0
[11 empty] | 2023-04-10 | 8 | 2 | 0 | 0
[11 empty] | 2023-04-11 | 9 | 2 | 0 | 0
[11 empty] | 2023-04-12 | 10 | 2 | 0 | 0
[11 empty] | 2023-04-13 | 11 | 2 | 0 | 0
[11 empty] | 2023-04-14 | 12 | 2 | 0 | 0
[11 empty] | 2023-04-15 | 13 | 1 | 1 | 0
[11 empty] | 2023-04-16 | 14 | 1 | 1 | 0
[11 empty] | 2023-04-17 | 15 | 0 | 2 | 0
[11 empty] | 2023-04-18 | 16 | 0 | 0 | 2
[11 empty] | Entrega 3 |  |  |  |  | Cumulative Flow Diagram (CFD)
[11 empty] | Fecha | Day | To do | In Progress | Done
[11 empty] | 2023-05-06 | 1 | 1 | 1 | 0
[11 empty] | 2023-05-07 | 2 | 1 | 3 | 0
[11 empty] | 2023-05-08 | 3 | 1 | 3 | 0
[11 empty] | 2023-05-09 | 4 | 1 | 3 | 0
[11 empty] | 2023-05-10 | 5 | 1 | 3 | 0
[11 empty] | 2023-05-11 | 6 | 0 | 4 | 0
[11 empty] | 2023-05-12 | 7 | 0 | 0 | 4
Note on D14: ====== ID#AAAAxqdAIKo tc={DADC0938-BBFF-FE42-972C-FD36D536A50C} (2023-05-23 21:13:36) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: La eficiencia la calculamos con el Cycle Time Reply: (Touch time/Cycle time)*100
Note on F14: ====== ID#AAAAxqdAIKk tc={34393533-589B-BF43-B9DC-477782BCD312} (2023-05-23 21:13:36) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WIP/Lead Time en días